## Sheet1
S. No. | High Level Category | Tasks | Included in EY Approach | Owner | Estimate | Techical Upgrade | Customized Components | Comments
1 | Infrastructure upgrade | Infrastructure Upgrade Obtain & review Supported Software Matrix for Guidewire Data Management Provision New Hosts as Needed IPS + BODS Database server(s) Get New Software SAP - IPS - Program - Documentation - Data Services - Program - Documentation Java Guidewire DataHub - BASE as needed - UPGRADE - (Optional) All interim releases from BASE to UPGRADE, depending on database schema merge approach (Optional) Setup new hosts | Yes
2 | Testing Plan | Include all targets: DataHub itself and any/all downstream integrations Regression Need to prove, comprehensively & efficiently, that after modifications, same remains same Suggested technique Get a handle on what source data is going to be used for testing. Should be stable / static / fixed. Use GXR Of, if not using GXR... - Create matching pairs of views on CURRENT and UPGRADED tables and views - Eliminate / resolve transient data - Date-time metadata - Surrogate keys - With identical schemas - If there are legitimate field length exceptions, use the larger length - If source data can't be stabilized, views can constrain on dates or data subsets to filter-down to stable data - (Or... just use GXR. Same principles.) - Create master script to compare content in pairs of views New Development (from UPGRADE) Not covered here -- use existing tools & methods
3 | Code Upgrade: Folder Structure | Difference Detection Manual Inspection Tooling Just use manual inspection Can make use of Windows "tree" command, if you like Or diff tool, like Araxis or WinMerge Comments Foundational but general trivial task. Setup new folder structure according to UPGRADE product requirements, adding whatever extensions were used and you want to carry forward. | Yes?
4 | Code Upgrade: Database Schemas | Objective: creation of three scripts (or sets of scripts). This "three scripts or sets of scripts" is just a suggestion, but forms, I think, a good way to organize and think about it. 1: OOTB BASE 2: Upgrade from OOTB BASE > OOTB UPGRADE. Delta DDL script. 3: Addition of customer extensions to UPGRADE Two Issues: collisions & duplicates - Duplicates: different names but same meaning. It's entirely possible for customer to add a table, index, view, column, or other object which is a duplicate in terms of business meaning with a new object in UPGRADE. These need to be hunted down and resolved manually. - Collisions: same name, different meaning or structure Otherwise, apart from redundancy, if customer extensions were kept separate all along vis-a-vis BASE, then, generally speaking, it should be easy to enough to apply them atop UPGRADE (script #2). Methods to come by the two delta DDL scripts Option 0: Use merge capabilities in modeling tool. If a powerful modeling tool with merging capabilities is present (PowerDesigner has this), then use it. Option 1: Use a 3rd party "compare"-type tool ApexSQL Compare RedGate SQL Compare Etc. Option 2: Leverage Existing Delta DDL For BASE > UPGRADE: download all the individual Guidewire DataHub & InfoCenter software packages between BASE and UPGRADE. Harvest all the individual sets of upgrade DDL for each version and assemble into one file or set of files. For BASE > CURRENT: if the customer has kept their extension DDL scripting segregated, then they're all set. If not... back to using option 1 or 3 for the BASE > CURRENT delta. Option 3: Manual Grind Scripts, diff tool, hand-write DDL - Easy to script-out schema objects into a folder, with separate files for each object - Can then point diff tools like Araxis at the two sets of files - But creating actual delta DDL would still be manual With dbms catalog querying - Easy enough to write dbms catalog queries to find new tables, new columns, etc. - But then would have to manually write delta DDL (unless you got real fancy with the dynamic SQL -- would make more sense to buy 3rd party compare tool) Suggested method Create BASE > UPGRADE delta DDL script Create BASE > CURRENT delta DDL script Identify collisions "Collision": by name, same object was added. Can't add twice -- can't exist in both BASE > CURRENT and BASE > UPGRADE scripts. o - Tables and views - Query to report on tables existing in BASE > CURRENT delta and BASE > UPGRADE delta to compare their logical structure (mostly, columns) - SQL Server: 1 - Oracle: 1 - Same table, new columns - Customer extension columns will typically begin with 'Z' or 'Z_', but possible that convention wasn't followed - Query: show identically-named columns existing in both deltas (BASE > CURRENT and BASE > UPGRADE) in, of course, OOTB BASE tables, and their possibly varying column characteristics. - SQL Server: 1 - Oracle: 1 - Indexes - Characteristics to look at - Columns - Column order - Uniqueness - Index type - Foreign key constraints Identify business duplicates Tables and views with different names but identical or substantially overlapping columns - Query to report on tables existing in BASE > CURRENT delta and BASE > UPGRADE delta with "substantially overlapping" (define) sets of columns - SQL Server: 1 - Oracle: 1 Same table, new columns - Customer extension columns will typically begin with 'Z' or 'Z_' - But, may be redundant with new OOTB UPGRADE columns - Query: strip-off the 'Z' and 'Z_' from the front of BASE > CURRENT columns for BASE OOTB tables and combine, for manual comparison, with BASE > UPGRADE delta columns. - SQL Server: 1 - Oracle: 1 Indexes - Indexes have lots of properties, but if certain characteristics are duplicate, then the indexes are likely themselves duplicate - Characteristics to look at - Columns - Column order - Uniqueness - Index type - Query: identify duplicate (or at least very similar) indexes that are candidates for merging Foreign key constraints - Identifying these should come out of analysis of both name collisions and business duplicates - Deal with manually, merging Deal with collisions. Modify BASE > CURRENT and BASE > UPGRADE delta DDL script(s), merging and eliminating. Given the presumption in favor of using OOTB UPGRADE objects, it's likely that only modifications to BASE > CURRENT will be needed, deferring to what's in UPGRADE. Objective is to create a single script (or set of scripts, if prefer to break up) to apply customer extensions to pure, OOTB UPGRADE. Make a note of dropped and modified objects for ETL and downstream code fixing. - Extraction - TRF - ODS - Downstream Deal with business duplicates. Modify BASE > CURRENT and BASE > UPGRADE delta DDL script(s), merging and eliminating business duplicates. Given the presumption in favor of using OOTB UPGRADE objects, it's likely that only modifications to BASE > CURRENT will be needed, deferring to what's in UPGRADE. Make a note of dropped and modified objects for ETL and downstream code fixing. - Extraction - TRF - ODS - Downstream | [5 empty] | Which option matches with our approach?
5 | Code Upgrade: Build-out regression testing comparison views | As soon as the merged DDL is ready, can build out the pairs of views for regression testing, although, of course, the new targets won't be populated yet.
6 | Code Upgrade: Metadata Table Contents (via DML Script) | Similar problem to delta DDL, but much simpler Tables MD_CVRBL_TYPE MD_FK_REF MD_JUNK_DIM Build superset (union) of everything in CURRENT + UPGRADE Query: dynamic SQL forming unioned set of records from these three tables. SQL Server: 1 Oracle: 1 If collisions or business duplicates result in need for modification: modify. Would almost certain need to modify MD_* table contents in the event of business duplicates. Suggest getting this DML out of OOTB scripts, where it's inappropriately intermingled with DDL.
7 | Code Upgrade: Other Guidewire files | Commit-Rollback Data dictionary Data specifications -- manuall compare and merge Worksheets Worksheet Schemas Worksheet Contents Navigation Data contents COMMON folder contents DIAL binaries XML and JSON configuration files DATAIN contents UserETLConfig.xls, RefDataConfig.xls -- manually compare & merge RefDataEntry.xls Worksheets - Numerous - Make lists using macro / VBA - Then compare to identify the two standard delta sets: BASE > CURRENT (customer extension) and BASE > UPGRADE - Same issues apply, re: collisions and business duplicates. Deal with manually. "Collisions" = same reference entity name. (Mean the same?) "Business duplicates" = the same thing by different names. Worksheet contents - Fairly straightforward to find what's missing via Excel formulas (COUNTIF, VLOOKUP, etc.) - Just copy-and-paste to assemble. SHELLSCRIPTS folder contents
8 | Code Upgrade: BODS ETL Code Objects | If *not* using GW ETL code extension standards Preliminary Setup Developer setup: for maximum efficiency, the developer handling the merge should be enabled to run two simultaneous BODS Designer sessions with different local repositories open on each, viewing each simultaneously on large monitors (at least 21"). * Remote-in to two VMs? * Remote-in to the same Windows job server in two sessions (as two different users)? * Two simultaneous Citrix sessions? Guidewire recommends setting up configs explicitly called 'Base', 'Current', and 'Upgrade', with matching local repositories: LREPO_BASE, LREPO_CURRENT, and LREPO_UPGRADE. Scripts are [or will be] provided that assume these exact names. Of course, you could also use existing configs and treat these "base", "current", and "upgrade" names as merely logical names. But working through an upgrade can be picky and get confusing, and going to the trouble of creating configs and repositories with these exact names is advised. If you haven't already, organize OOTB Guidewire products under X:\GWDM\PRODUCTS\GUIDEWIRE\ Create central repositories: CREPO_BASE_VS_UPGRADE CREPO_BASE_VS_CURRENT CREPO_OOTB_[X_X_X] if it doesn't already exist, and where the X's are replaced with the tripartite version of the software that represents the last version to which the customer has upgraded. For example, if the customer originally installed DataHub 8.3 and then successfully upgraded to 9.0 and then 9.1, and is now looking to upgrade to version 10.0.0, you would create CREPO_OOTB_9_1_0. We will hereinafter refer to this repo as "CREPO_BASE". We will assume that current development is limited to a single branch, and whatever the actual name of that branch's central repository, we will refer to it here as "CREPO_BRANCH". We assume that "CREPO_BRANCH" holds the ongoing commits of ETL code during normal development. Load LREPO_BASE with OOTB base code Load LREPO_UPGRADE with OOTB upgrade code Make list of objects dropped in the upgrade vs. the base: "Dropped in Upgrade". - Query: look for objects by name-and-type in LREPO_BASE which don't exist in LREPO_UPGRADE. (Want to do this before we start to use either of these local repositories.) - SQL Server: 2 - Oracle: 2 Load all three central repositories with base code from LREPO_BASE with commit comment 'Base'. Note: all three central repositories start with BASE code. Per the assumptions: declare a code freeze -- no commits to the current branch until upgrade complete. Load/refresh LREPO_CURRENT with current code from the branch's central repo If you haven't already, at this point, establish the three Designer sessions, opening LREPO_BASE, LREPO_UPGRADE, and LREPO_CURRENT in each, respectively. Note: in all the following, datastore objects should be excluded/ignored, although not the children thereof. Build-up central repo CREPO_BASE_V_UPGRADE In the "Upgrade" session, with LREPO_UPGRADE open Activate CREPO_BASE_VS_UPGRADE Attempt to add everything from LREPO_UPGRADE to CREPO_BASE_VS_UPGRADE. Designer won't let you add objects already present. For objects it does let you add, use comment 'Upgrade New v Base'. Do this in batches by object type, in this order: formats > datastore children (tables + template tables + functions) > user-defined functions > dataflows > workflows > jobs > projects. When doing this, do not select the "and dependents" option. Perform a checkout-without-replacement of everything into LREPO_UPGRADE from CREPO_BASE_VS_UPGRADE. Do this in batches as above. Check everything back in. Designer should notice both change and lack-of-change. On lack-of-change, Designer will simply reverse checkout, and you will will still have only one code version in central with 'Base' or 'Upgrade New v Base' comments. For anything changed, will end up with two versoins in CREPO_BASE_V_UPGRADE. On check-in of changed objects, use comment 'Upgrade Changed v Base'. We now know what's both unchanged, new, and changed in the upgrade vs. the base. Will be able to write queries using these commit comments. Build-up central repo CREPO_BASE_V_CURRENT In the "Current" session, with LREPO_CURRENT open Activate CREPO_BASE_VS_CURRENT Attempt to add everything from LREPO_CURRENT to CREPO_BASE_VS_CURRENT. Designer won't let you add objects already present. For objects it does let you add, use comment 'Current New v Base'. Perform a checkout-without-replacement of everything into LREPO_CURRENT from CREPO_BASE_V_CURRENT, as above Check everything back in, as above. On check-in of changed objects, use comment 'Current Changed vs. Base'. Merge Code Can either work in LREPO_UPGRADE or LREPO_CURRENT. In general, it makes sense to work in the repository with the higher number of (new + non-colliding changed) objects, to minimize effort. We will assume that LREPO_CURRENT holds that overall -- that the BASE > CURRENT delta is bigger than the BASE > UPGRADE delta. Make list: "Change Conflicts": objects changed in both CREPO_BASE_V_CURRENT and CREPO_BASE_V_UPGRADE - Query - SQL Server: 2 - Oracle: 2 Make list: "New Conflicts": objects new, by name, in both CREPO_BASE_V_CURRENT and CREPO_BASE_V_UPGRADE - Query - SQL Server: 2 - Oracle: 2 Make list "Conflicts": "Change Conflicts" UNION "New Conflicts" - Query - SQL Server: 2 - Oracle: 2 Make list "Upgrade No Conflict": the 'Upgrade Changed vs Base' objects in CREPO_BASE_V_UPGRADE which are not marked 'Current Changed vs Base' in CREPO_BASE_V_CURRENT unioned with the objects "Upgrade New vs Base" that are not in the "New Conflicts" list. - Query - SQL Server: 2 - Oracle: 2 Activate CREPO_BRANCH From CREPO_BRANCH, into local repository LREPO_CURRENT, checkout objects in list "Conflicts". Activate CREPO_BASE_VS_UPGRADE For each object 'Upgrade No Conflict' -- perform a 'Get Latest' from CREPO_BASE_VS_UPGRADE. As above & per standard, work from the bottom up: formats > datastore children > functions > dataflows > workflows > jobs > projects. (Check if can be automated.) Activate CREPO_BRANCH For each object in 'Upgrade No Conflict' perform a 'Checkout Without Replacement' For objects in the Conflicts list, need to do a Detailed Merge Detailed Merge Process For objects in 'Conflicts' list - Objective here is to get merged, functional (at least unit tested) code into CREPO_BRANCH - Work from bottom up (formats & datastore children > functions > etc.) - Determine which object version, current or upgrade, has more changes vs. base. Want to recode as little as possible. - How? Can either decide based on simple visual inpsection, or go to the trouble of doing diffs and inspecting those. If need to do diffs... - In Upgrade session... - - Activate CREPO_BASE - - Compare object against central repository - - Inspect diff to get a sense of / details about the changes in upgrade vs. base - In Current session - - Activate CREPO_BASE - - Compare object against central repository - - Inspect diff to get a sense of / details about the changes in current vs. base - If Current holds more changes, modify it, merging the changes in Upgrade. - In Upgrade session, learn the changes in Upgrade vs. Base - Activate CREPO_BASE - Compare object against central repository - Inspect diff to get details about the changes made by Guidewire in upgrade vs. base - Can always replicate a local object and then 'Get Latest' from central to have both objects side-by-side in local, for full visual inspection (if Designer's diff is inadequate) - In Current session, working in LREPO_CURRENT - Object should already be checked-out from CREPO_BRANCH - If you want to get the Upgrade version of the object in the Current local repository so you have both objects in the same local repo side-by-side (to accommodate, for instance, copy-and-paste); this is a judgment call, and may be more trouble than it's worth. - - In the Upgrade session... - - Replicate the object in question to [object_name]_UPG - - Get object into LREPO_CURRENT by whatever means you prefer - - "Bounce" it off CREPO_UPGRADE_VS_BASE (and then delete it from that central repository) - - Repository-to-repository export-import (note the need to perform local object library refresh afterwards) - - File export > import - Merge changes from Upgrade into Current object - OR, if Upgrade has many more changes vs. Base than Current, modify Upgrade, including the changes present in Current. - Still working in LREPO_CURRENT - Replicate object in question as [object_name]_CUR - Activate CREPO_UPGRADE_VS_BASE - Perform 'Get Latest' on object in question - I believe we can we do this to a local object in a checked-out state. (Was checked-out object from CREPO_BRANCH.) - If we can't, then we can do export-import via XM or direct repository-to-repository - (It is not recommended to try to simultaneously bring into conformance with extension standards during an upgrade; upgrades are complicated enough as-is. Take "bring into conformance" as a separate project.) - In Designer, open both [object_name]_CUR and the just-retrieved Upgrade version of the object, compare, and merge into [object_name]. - Once satisfied with the merge, delete [object_name]_CUR Test Integration (full job run sequences) testing Perform (data) regression testing per plan - Build-out new target with merged DDL and DML (for MD_* table contents) - As needed, build-out old ("CURRENT" before merge) targets for comparison - Load pre- and post-merge targets with pre- and post-merge code - If not yet done, build-out comparison views - Perform data comparisons - Resolve problems, cycle to acceptance, etc. Commit to branch Files ETL code, working from bottom up, no dependents: adds and check-ins. - First, perform adds of objects identified as "Upgrade New vs Base" which were not on the "New vs New Conflict" list. Suggest using commit comment "New in upgrade to version [X.X.X]". - Then, perform check-ins of all checked-out objects, again working from the bottom up. Suggest use commit comment "Merged changes from upgrade to version [X.X.X]". If Using GW ETL Coding Extension Standards To Do
9 | Code Upgrade: Downstream integrations | Modify as needed Perform (data) regression testing per plan Build-out new target with merged DDL and DML (for MD_* table contents) As needed, build-out old ("CURRENT" before merge) targets for comparison Load pre- and post-merge targets with pre- and post-merge code If not yet done, build-out comparison views Perform data comparisons Resolve problems, cycle to acceptance, etc.