## BA Activities & Best practice
Inception Phase
1 | Migration Scope | 1. To understand the migration scope in terms of number of systems, years. 2. To understand the function scope of data in terms of business providers, agency, downstream system flows. 3. Reason for migration with respect to a. decommisioning of legacy systems, b. deploying of latest application, c. modernizing legacy platforms out of support. d. Upgrading to Cloud e. Shift to central Database
2 | Time line of Migration scope | 1. When do you need to complete the migration 2. Time based migration for each system, business, LOB, other factors.
3 | Legacy system Architecture | 1. Understanding the legacy architecture including the downstream systems 2. Identifying the legacy systems for migration 3. Requiremnt of LOB 4. Downstream systems impacted by migration 5. Data flow to/fro from new system to legacy systems
4 | Archiving requirements | 1. Understanding the scope of data migration in terms of a. Open Claims b. Closed Claims migration for past 5 years c. Closed claims migration for past 10 years 2. Archiving requirement for data a. Defining retention period b. Storing data in different systems c. Dumping data in static database
5 | Data Strategy | 1. Big Bang migration 2. Phase migration
6 | Identifying the target load methology | 1. Claim Migration tool 2. CCST staging load by OOTB batch job 3. GW API load 4. Identify the ETL tool
Sprint 0
6 | Re-estimating User stories and timelines | 1. Re-estimating if required based on requirements gathered during inception
7 | Creating User stories, sprint backlogs | 1. Creating backlogs with epic, features,user stories, tasks
8 | Conceptual Sprint planning | 1. Identifying sprint dependency with the other project team such as configuration, Integration. 2. Alligning stories to all the sprints
Sprint level activities
9 | Functional Gap analysis | 1. Understanding the functionality by identifying the fucntional terminology, functional flows. 2. Gathering requirement in each subject area of claim graph a. Claim First notice of Loss b. Coverage c. Incident d. Exposure e. Payments d. Policy f. Matter, Litigation, Negotiation g. Deductibles
10 | Legacy UI application | 1. Legacy claim system user interface understanding 2. Gathering the flow of FNOl, Claims search 3. Third party payment integration
11 | Source data model schema | 1. Understand the basic of source schema with help of client SME is must to begin the analysis. 2. Identifying the entity relationship of source entities.
12 | Source data quality checks | 1. Identifying the data quality issues during analysis a. Quality compromised for older claims b. null values in mandatory attributes c. Integrity failures - Lack of referential integrity d. Hidden/Ambigous data e. Lack of record uniqueness f. Duplicate claim numbers g. No consistency between multiple source h. Data completeness
13 | Data profiling & Source analysis | 1. Identifying different data scenarios for analysis a. line of business b. Systems c. Business type - third party claims, self-insured claims d. Claim intake - Claim raised by portal, by agents etc 2. Analyse data for complexity of data 3. Scope for cleansing
14 | Reference Typelist analysis | 1. To conform all reference drop downs and map against GW typelist typecodes 2. In case of multiple source systems, multiple mapping between each system against GW typelist needs to be perfromed 3. Ex: Policy type, LOB code, Jurisdiction etc
15 | Creating transformational rules | 1. Extarction logic from source with joins, where conditions, group by, order by 2. Custom rules for every attribute of entity to map to target with specific validation rules, target date formats 3. TRF rules includes casting of datatype, formating dates, 4. different case scenarios for TRF with case when statements 5. Hardcoding values in attributes based on business scenarios
16 | Source and Target Validation rules | 1. Source technical validations to confirm the data quality, data completeness, uniqueness and integrity 2. To understand custom business requirement that could be framed as business validation rules which mitigates the errors during migration execution 3. To implement target validation technical rules - non-null checks, unique contraint checks, integrity checks etc from Claimcenter perspective 4. To implement target business rules such as presence of mandatory contact roles, loss date between policy effective and expiration date etc. 5. BAs have to gather configuration validation rules implemented in every sprint to implement the business validation rules and mitigate errors during migration.