## Sheet1 (hidden)
Policy
Inventory For data studio Estimate (PC) | No of Inventory | ADBT Effort In hrs
OOTB Auto curated Datasets Updated | 30 | 300
OOTB Business ready curated Datasets updated | 3 | 150
New Auto curated datasets to be created | 0 | 0
New Business Ready cuarted datasets to be created | 0 | 0
Audit and Recon |  | 200
Total in hrs |  | 650 | 73.4463 | 22.0339
Claims
Inventory For data studio Estimate
OOTB Auto curated Datasets Updated | 30 | 300
OOTB Business ready curated Datasets updated | 4 | 200
New Auto curated datasets to be created | 10 | 200
New Business Ready cuarted datasets to be created | 2 | 150
Audit and Recon |  | 200
Total in hrs |  | 1050
Inventory for Explore(Only PC)
OOTB Policy Liveboards to be updated | 8 | 240
New Policy Liveboards to be created | 0 | 0
OOTB Policy Worksheets to be updated | 3 | 150
OOTB Report update | 30 | 300
New Policy report creation | 0 | 0
Total in hrs |  | 690 | 77.9661 | 23.3898
Grand total in hrs |  | 1340

## Assumptions
ASSUMPTIONS
assumed 80 claims Reports will be created in Explore .Source of data will be Ivos (SQL server on-prem) | 80
Simple(50%) | 40
Medium(30%) | 24
Complex(20%) | 16
assumed 30 Liveboards will be created in Explore | 30
Simple(50%) | 15
Medium(30%) | 9
Complex(20%) | 6
Only Claims data is in scope
External 3rd party data push to Data studio and non core data creation in Datastuido or explore is out of scope in this estimation
semi-structure or Unstructure data curation and remidiation in Data studio or Explore is Out of scope
MSMM will enable the datastudio and Explore access
30 Claims Autocurated datasets and 10 Business Ready curated data sets (OOTB(4) and Custom)

## Questions (hidden)
Are there any support from MSMM for gap analysis
How much dimensions and facts are in existing reports
what are the type of sources and how many source tables involved
how many measures report wise
are there any reports built on DWH systems
are there any views/aggregated materlized views if any
what is the BI tool used
is there any report specification/data model document for the ivos reports
are there any 3rdparty data need to be integrated
what is the timeline for this programme and when the gap analysis to be started

## Explore_Datastudio
Phases | Effort in Hrs
Explore ADBT effort in hrs | 1779.2
Datastudio ADBT effort in hrs | 2413.88
Gap Analysis(Inception) | 209.654
PMO(scrum master,Lead,Architect) | 838.616
Total in hrs(ADBT,Gap analysis,PMO) | 5241.35

## Explore
Phase(DBUT) | Complexity | No. of Reports |  | No of Worksheet |  | No of Formulas |  | No of Tables |  | Export/import |  | Filters |  | Total in hrs
|  | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs
Per LiveBoard | Simple | 3 | 0.5 | 2 | 0.3 | 2 | 0.3 | 2 | 0.3 | 1 | 0.15 | 2 | 0.3 | 5
| Medium | 5 | 0.5 | 4 | 0.6 | 4 | 0.6 | 4 | 0.6 | 3 | 0.45 | 4 | 0.6 | 7
| Complex | 7 | 1.05 | 6 | 0.9 | 6 | 0.9 | 6 | 0.9 | 7 | 1.05 | 6 | 0.9 | 9
TOTAL(HRS) | 10.9 |  | 2.05 |  | 1.8 |  | 1.8 |  | 1.8 |  | 1.65 |  | 1.8
Phase(DBUT) | Complexity | No. of KPIs |  | No of Worksheet |  | No of Columns/Attributes |  | No of Tables |  | No of Joins |  | Filter/Parameters |  | Formulas |  | Total in hrs
|  | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs
Per Reports | Simple | 3 | 0.9 | 1 | 0.2 | 10 | 1.5 | 2 | 0.3 | 1 | 0.3 | 3 | 0.9 | 2 | 0.3 | 7
| Medium | 5 | 1.5 | 2 | 0.3 | 20 | 6 | 4 | 1.2 | 3 | 0.9 | 5 | 1.5 | 4 | 1.2 | 12
| Complex | 7 | 3.15 | 4 | 0.45 | 30 | 9 | 6 | 1.8 | 5 | 1.5 | 7 | 3.15 | 6 | 2.7 | 22
TOTAL(HRS) | 38.75 |  | 5.55 |  | 0.95 |  | 16.5 |  | 3.3 |  | 2.7 |  | 5.55 |  | 4.2
Reports | 80 | Effrot(in hrs)
Simple(50%) | 40 | 280
Medium(30%) | 24 | 288
Complex(20%) | 16 | 352
Total in hrs |  | 920
Liveboards | 30 | Effrot(in hrs)
Simple(50%) | 15 | 75
Medium(30%) | 9 | 63
Complex(20%) | 6 | 54
Total in hrs |  | 192
Explore effort Grand Total in hrs |  | 1112
Analysis |  | 333.6
QA |  | 222.4
Deployment |  | 111.2
Grand Total |  | 1779.2

## DataStudio
Phase(ADBT) | Complexity | No. of joins |  | No of Datasets |  | No of Columns/Attributes |  | No of Raw Tables |  | Export/import |  | Filters |  | Total in hrs
|  | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs | Elements | hrs
Per Autocurated datasets | Simple | 3 | 0.5 | 2 | 0.3 | 2 | 0.3 | 2 | 0.3 | 1 | 0.15 | 2 | 0.3 | 3
| Medium | 5 | 0.5 | 4 | 0.6 | 4 | 0.6 | 4 | 0.6 | 3 | 0.45 | 4 | 0.6 | 6
| Complex | 7 | 1.05 | 6 | 0.9 | 6 | 0.9 | 6 | 0.9 | 7 | 1.05 | 6 | 0.9 | 9
TOTAL(HRS) | 10.9 |  | 2.05 |  | 1.8 |  | 1.8 |  | 1.8 |  | 1.65 |  | 1.8
Phase(ADBT) | Complexity | No. of joins |  | No of Transformations/Sql Query |  | No of Columns/Attributes |  |  |  | Export/import |  | Filter/Parameters |  | Functions |  | Total in hrs
|  | Elements | hrs | Elements | hrs | Elements | hrs |  |  | Elements | hrs | Elements | hrs | Elements | hrs
Per Business Curated Datasets | Simple | 3 | 0.9 | 1 | 0.3 | 15 | 15 |  |  | 1 | 0.3 | 3 | 0.9 | 2 | 0.6 | 18
| Medium | 5 | 2.25 | 2 | 0.9 | 25 | 25 |  |  | 3 | 0.9 | 5 | 2.25 | 4 | 1.8 | 33.1
| Complex | 7 | 10.5 | 4 | 6 | 40 | 40 |  |  | 5 | 1.5 | 7 | 7 | 6 | 1.2 | 66.2
TOTAL(HRS) | 117.3 |  | 13.65 |  | 7.2 |  | 80 |  |  |  | 2.7 |  | 10.15 |  | 3.6
Autocurated datasets | 30 | Effrot(in hrs)
Simple(50%) | 15 | 270
Medium(30%) | 9 | 297.9
Complex(20%) | 6 | 397.2
Total in hrs |  | 965.1
Business Curated Datasets | 10 | Effrot(in hrs)
Simple(40%) | 6 | 108
Medium(30%) | 3 | 99.3
Complex(30%) | 2 | 132.4
Total in hrs |  | 339.7
Data Studio effort Grand Total in hrs(DBUT) |  | 1304.8
Analysis |  | 587.16
QA |  | 391.44
Deployment |  | 130.48
Data Studio effort Grand Total in hrs |  | 2413.88